## Sheet1
reduction sectors 1 – 5 for CDIPS status file / notes
projid	sector	cam	ccd	status	comment
1300	2	1	1	done	Sector 2
1301	2	1	2	done
1302	2	1	3	done
1303	2	1	4	done
1304	2	2	1	done
1305	2	2	2	done
1306	2	2	3	done
1307	2	2	4	done
1308	2	3	1	done
1309	2	3	2	mostly done (LCs done). Got a astromrefglob bug in final assessment.
1310	2	3	3	done
1311	2	3	4	done
1312	2	4	1	2019/04/16, ~2pm. Finished! With 4.2Tb 89% on phtess1. (Though this is including all the new frames from ccds2-4 as well). 2019/04/15. attempting to rerun! Starting with 4.7Tb, 88% on phtess1. 2019/03/06 failed b/c of astrometry bug on photref
1313	2	4	2	2019/04/15. attempting to rerun! Starting with 4.7Tb, 88% on phtess1. 2019/03/06 failed b/c of astrometry bug on photref
1314	2	4	3	2019/04/15. attempting to rerun! Starting with 4.7Tb, 88% on phtess1. 2019/03/06 failed b/c of astrometry bug on photref
1315	2	4	4	2019/04/15. attempting to rerun! Starting with 4.7Tb, 88% on phtess1. 2019/03/06 failed b/c of astrometry bug on photref
1316	3	1	1	“done” but RMS vs mag is crap. Will need to be redone?!?!. Seems like bad points/times arent being correctly masked. Visible by-eye outliers will need to be fixed…	Sector 3. got bkgd subtracted. Stopped 20190320 b/c of engineering data missing. Restarting w/ hack to make the pickles work 20190320. Should complete sector 3 2019/03/26 if it works…
1317	3	1	2	bug in astrometric shifting. No Lcs. WCS errors? Shifting error vs CRPIX from SPOC???
1318	3	1	3	“done” but RMS vs mag is crap. Will need to be redone?!?!.
1319	3	1	4	“done” but RMS vs mag is crap. Will need to be redone?!?!.
1320	3	2	1	“done” but RMS vs mag is crap. Will need to be redone?!?!.
1321	3	2	2	bug in astrometric shifting. No Lcs. WCS errors? Shifting error vs CRPIX from SPOC???
1322	3	2	3	bug in astrometric shifting. No Lcs. WCS errors? Shifting error vs CRPIX from SPOC???
1323	3	2	4	“done” but RMS vs mag is crap. Will need to be redone?!?!.
1324	3	3	1	“done” but RMS vs mag is crap. Will need to be redone?!?!.
1325	3	3	2	“done” but RMS vs mag is crap. Will need to be redone?!?!.
1326	3	3	3	NOVEL BUG, NO LCS
1327	3	3	4	“done” but RMS vs mag is crap. Will need to be redone?!?!.
1328	3	4	1
1329	3	4	2
1330	3	4	3
1331	3	4	4
1332	4	1	1
1333	4	1	2
1334	4	1	3
1335	4	1	4
1336	4	2	1
1337	4	2	2
1338	4	2	3
1339	4	2	4
1340	4	3	1
1341	4	3	2
1342	4	3	3
1343	4	3	4
1344	4	4	1
1345	4	4	2
1346	4	4	3
1347	4	4	4
1348	5	1	1
1349	5	1	2
1350	5	1	3
1351	5	1	4
1352	5	2	1
1353	5	2	2
1354	5	2	3
1355	5	2	4
1356	5	3	1
1357	5	3	2
1358	5	3	3
1359	5	3	4
1360	5	4	1
1361	5	4	2
1362	5	4	3
1363	5	4	4
1364	1	1	1
1365	1	1	2
1366	1	1	3
1367	1	1	4
1368	1	2	1	“done” early. Some bimodality seen at bright end of RMS vs mag. Also was done with incorrect “badtimes” masked out. Probably should be redone
1369	1	2	2
1370	1	2	3
1371	1	2	4
1372	1	3	1
1373	1	3	2	“done” early. Some bimodality seen at bright end of RMS vs mag. Also was done with incorrect “badtimes” masked out. Probably should be redone
1374	1	3	3
1375	1	3	4
1376	1	4	1
1377	1	4	2
1378	1	4	3
1379	1	4	4